## Sheet1
Week | <component>
2026-02-03 | GitHub Repository And Python App
2026-02-03 | Unit Tests And Linting
2026-02-10 | CI/CD Pipelines
2026-02-10 | Deployment and validation
2026-02-10 | ReadMe And Documentation
Goals
2026-02-03 | Create Repo, scaffold python flask app, add make file and requirements.txt
2026-02-03 | Write Basic test cases and run lint checks.
2026-02-10 | setup github actions CI and Azure Pipeline CD
2026-02-10 | Deploy App to Azure App Service, Test API, Capture Screenshots
2026-02-10 | Complete ReadMe, add trello link, spreadsheet link and screencast.